Dropshipping July Project Plan

Python Research Tool + GitHub Repo + Store Rebuild + Product Testing

Prepared for Jason Mullen | Main project for July 2026

Project Mission: Build a repeatable product-research system that helps you find dropshipping products with trend demand, realistic selling prices, and enough profit margin to test responsibly. The first July goal is not instant passive income; it is creating a disciplined system that can eventually become semi-passive after testing, optimization, and repeatable operations.

| Area | Decision |
| --- | --- |
| Business goal | Create a data-informed dropshipping business that can become a serious side-income project. |
| Old store lesson | Do not rebuild the gymwear store blindly. Validate product demand and profit first. |
| Main build | A Python program called Dropship Trend Finder. |
| Core output | A ranked CSV of product opportunities labeled TEST, WATCH, or PASS. |
| Data approach | Use cleaner sources: supplier CSV, Reddit RSS, and optional eBay Browse API. Avoid random scraping of protected sites. |
| GitHub goal | Push the project to a clean public or private GitHub repo with a README and frequent commits. |
| July finish line | Working program, GitHub repo, 30-50 researched products, one chosen niche, rebuilt store, and 3-5 small product tests. |

# 1. Project Objective

Create a smoother, more serious dropshipping project by building the research system before spending time rebuilding the store. The Python tool should help answer one question:

“Is this product worth testing, or am I guessing?”

Build a Python program that gathers product trend signals and estimates profit.

Use the program to rank products instead of choosing random items from videos.

Push all code to GitHub so the project becomes a real portfolio/business asset.

Rebuild the store only after product research shows a clear niche and offer.

Test products with small budgets, then kill weak products quickly and improve strong ones.

# 2. Business Model: Simple Flow

Collect supplier products with cost, shipping, category, keyword, and supplier link.

Measure trend interest using public sources and keyword chatter.

Check market pricing so the selling price is realistic.

Calculate estimated profit after cost, shipping, platform/payment fees, and ad cost.

Score each product and label it TEST, WATCH, or PASS.

Build a product page only for products that survive the scoring system.

Run small tests, measure results, and improve or kill the product.

Supplier Products → Trend Signals → Market Price → Profit Score → Product Page → Test Ads → Kill or Scale

# 3. The Python Program

Program name: Dropship Trend Finder

## 3.1 What the Program Does

Reads product ideas from data/supplier_products.csv.

Pulls trend chatter from public Reddit RSS feeds.

Optionally checks marketplace prices through the official eBay Browse API.

Uses your supplier costs to estimate profit and margin.

Ranks products with an opportunity score.

Exports a clean spreadsheet to output/opportunities.csv.

| Input / Output | File | Purpose |
| --- | --- | --- |
| Input | data/supplier_products.csv | Your product list with costs, shipping, selling price, supplier URL, and category. |
| Input | data/seed_keywords.txt | Extra keywords or niches to research. |
| Optional secret | .env | API tokens and assumptions such as ad cost and fee percentage. |
| Output | output/opportunities.csv | Ranked product list with estimated profit, margin, score, and action label. |
| Documentation | README.md | Explains setup, commands, scoring logic, and GitHub workflow. |

## 3.2 Minimum Product Data to Add

| Column | Meaning | Example |
| --- | --- | --- |
| product_name | Your name for the product | Resistance Band Set |
| keyword | Search phrase buyers might use | resistance bands |
| product_cost | Supplier cost before shipping | 6.50 |
| shipping_cost | Shipping/handling estimate | 2.50 |
| estimated_sale_price | Fallback selling price if no API is used | 24.99 |
| supplier_url | Where the product comes from | Supplier product link |
| category | Niche/category | fitness |

product_name,keyword,product_cost,shipping_cost,estimated_sale_price,supplier_url,category Resistance Band Set,resistance bands,6.50,2.50,24.99,https://example.com/resistance-band-set,fitness

# 4. Product Scoring System

The program should not just find “trendy” products. It should find products that have enough margin to test. Trend without profit is a trap.

| Score Component | Weight | What It Means |
| --- | --- | --- |
| Profit margin strength | 55% | Does the product still make money after cost, shipping, fees, and estimated ad cost? |
| Marketplace signal | 25% | Are there active listings and realistic selling prices? |
| Trend chatter | 20% | Are people talking about the keyword or problem? |

estimated_profit = sale_price - product_cost - shipping_cost - platform_fees - estimated_ad_cost profit_margin = estimated_profit / sale_price opportunity_score = 0.55 * margin_score + 0.25 * marketplace_score + 0.20 * trend_score

| Action Label | Meaning | Rule of Thumb |
| --- | --- | --- |
| TEST | Worth a small test | Profit margin is strong, demand signal exists, and product is not restricted or branded. |
| WATCH | Interesting but not ready | Some demand exists, but margin, price, or trust concerns need more research. |
| PASS | Do not waste time yet | Weak margin, weak demand, high shipping risk, legal/brand risk, or no clear buyer problem. |

Minimum TEST criteria: estimated profit of at least $10, margin around 30% or higher, a clear buyer problem/desire, no obvious copyright or brand-risk issue, and shipping that customers will tolerate.

# 5. July Roadmap

| Week | Main Goal | Tasks | Done When |
| --- | --- | --- | --- |
| Week 1 July 1-7 | Research engine | Run the Python project, add 30-50 supplier products, confirm scoring assumptions, and push the repo to GitHub. | The program runs and creates a ranked opportunities.csv file. |
| Week 2 July 8-14 | Validation dashboard | Add a simple Streamlit dashboard, track top candidates, add notes for pain point, hook, competitor, and product angle. | You can open a dashboard and see the top 10 opportunities clearly. |
| Week 3 July 15-21 | Store rebuild | Choose one niche, audit the old gymwear store, rebuild product page, FAQ, shipping policy, refund policy, and email capture. | The store looks trustworthy and can accept a test order. |
| Week 4 July 22-31 | Market testing | Test 3-5 products with small budgets, track traffic, add-to-cart, checkout, profit, and refunds. | Each tested product has a clear result: kill, improve, or scale carefully. |

# 6. Weekly Execution Checklist

## Week 1: Build the Research Engine

Download/open the dropship_trend_finder project folder.

Create a virtual environment and install requirements.

Run the program once with sample data.

Replace sample products with 30-50 real supplier products.

Check output/opportunities.csv for TEST/WATCH/PASS labels.

Create a new GitHub repo and push the project.

Commit at least 3 times this week with clear messages.

## Week 2: Improve Validation

Add columns for customer pain point, product hook, ad angle, competitor, and notes.

Build a basic Streamlit dashboard for the opportunities CSV.

Create a daily top 10 product shortlist.

Manually review the top 10 so the tool supports judgment instead of replacing it.

Improve the scoring formula if it rewards bad products.

## Week 3: Rebuild or Replace the Store

Pick one niche based on research instead of jumping between random products.

Audit the old gymwear store: homepage, product page, trust signals, photos, pricing, shipping, and checkout.

Decide whether to keep gymwear or pivot to a stronger niche.

Create one strong product page with a clear problem, benefit, proof, FAQ, shipping policy, and refund policy.

Set up email capture and basic abandoned-cart recovery if using Shopify.

## Week 4: Test and Review

Choose 3-5 products only. Do not test everything.

Create simple ad creatives/hooks for each product.

Track visitors, add-to-cart rate, checkout rate, cost per click, cost per purchase, profit, and refunds.

Kill products with weak margins or weak interest quickly.

Write a July review: what worked, what failed, what to improve in August.

# 7. Daily Work Rhythm

| Day | Focus | Output |
| --- | --- | --- |
| Monday | Product research | Add/update products in supplier_products.csv. |
| Tuesday | Python/code | Improve scraping/API logic, scoring, or dashboard. |
| Wednesday | Store/offer | Improve product page, copy, price, or trust signals. |
| Thursday | Validation | Review competitors, comments, pricing, and buyer pain points. |
| Friday | GitHub + review | Commit code, update README, summarize lessons. |
| Weekend | Deep work | Build dashboard, creatives, product pages, or test plan. |

# 8. GitHub Workflow

Create a new repo on GitHub first. Then run these commands from the project folder:

cd dropship_trend_finder git init git add . git commit -m "Initial dropship trend finder" git branch -M main git remote add origin https://github.com/YOUR_USERNAME/dropship-trend-finder.git git push -u origin main

For future updates:

git status git add . git commit -m "Improve product scoring" git push

# 9. Rules That Protect the Business

Do not rely on random scraping from sites that block bots or forbid automated collection.

Do not sell copyrighted, counterfeit, trademarked, medical-claim, dangerous, or restricted products.

Do not choose products only because a YouTube video says they are trending.

Do not test products with weak margins. Ads can destroy profit fast.

Do not scale a product until the data shows people actually buy it.

Order samples before seriously scaling so you know the quality, packaging, and shipping experience.

Keep customer trust high: clear shipping times, refund policy, contact email, and honest product photos.

# 10. Success Metrics

| Area | July Target |
| --- | --- |
| Python project | Runs successfully and creates output/opportunities.csv. |
| GitHub | Repo is pushed with README, clean folder structure, and multiple commits. |
| Research | 30-50 real supplier products reviewed. |
| Product shortlist | Top 10 products ranked with notes. |
| Store | One focused niche/storefront rebuilt or improved. |
| Testing | 3-5 products tested with small budgets. |
| Decision-making | Every tested product ends with a decision: kill, improve, or scale carefully. |

# 11. Next Upgrades After July

Add a Streamlit dashboard for easier product review.

Add Shopify Admin API integration for product upload later.

Add a database instead of relying only on CSV files.

Add daily scheduled reports once the scoring system is reliable.

Add competitor creative research manually or through permitted sources.

Add unit tests for scoring logic so changes do not break the tool.

# 12. Final Definition of Success

By July 31, success means: you have a working GitHub-backed Python product research tool, a ranked product opportunity spreadsheet, a clearer niche decision, a rebuilt or improved store, and real test data from 3-5 products. Even if no product is profitable yet, the month is successful if you stop guessing and build a system for making better decisions.

# Reference Notes

eBay Browse API: official marketplace search API for item summaries and pricing signals.

GitHub remote workflow: use git remote add origin to connect your local repo to GitHub.

Shopify Admin API: later upgrade for product/store integrations, not required for the first MVP.

pytrends note: avoid depending on pytrends as the core system because the repository is archived/read-only.